## Owner Allowances Cost
| Date Ordered | Vendor | Budget Allowance | Actual | Variance | Delivery Date
Windows (14 units, vinyl double-pane) |  |  | 12000 | 0 | 12000
Kitchen Cabinets - Main House (semi-custom) |  |  | 11000 | 0 | 11000
MIL Kitchenette Cabinets |  |  | 2500 | 0 | 2500
Bathroom Vanities (3 total: master double, guest single, MIL single) |  |  | 3500 | 0 | 3500
Countertop Materials & Labor (granite/quartz -- all areas) |  |  | 8500 | 0 | 8500
Interior Trim Material |  |  | 5200 | 0 | 5200
Cabinet & Drawer Hardware |  |  | 800 | 0 | 800
Exterior Doors (4 total) |  |  | 5500 | 0 | 5500
Interior Doors (11 total) |  |  | 4700 | 0 | 4700
Door Hardware |  |  | 1200 | 0 | 1200
Tile Material & Labor (3 shower surrounds + kitchen backsplash) |  |  | 8500 | 0 | 8500
Shower Doors - Glass (Master + MIL) |  |  | 1800 | 0 | 1800
LVP Flooring Materials & Labor (2,500 sqft) |  |  | 14000 | 0 | 14000
Kitchen Appliances - Main (range, fridge, dishwasher, microwave) |  |  | 6500 | 0 | 6500
Kitchen Appliances - MIL Suite (compact range + mini-fridge) |  |  | 2000 | 0 | 2000
Laundry Appliances (washer + dryer) |  |  | 2200 | 0 | 2200
Plumbing Fixtures (3 bath sets + 2 kitchen sinks) |  |  | 7500 | 0 | 7500
Lighting Fixtures |  |  | 9000 | 0 | 9000
Fireplace Materials (propane insert + surround) |  |  | 2500 | 0 | 2500
Exposed Wood Beam Material (6 beams, stained) |  |  | 2200 | 0 | 2200
Total |  |  | 111100 |  | 111100

## Payments
| Date | Amount
Build Contract Total |  | 449870
Payment Schedule:
1. Project Mobilization (10%) |  | 44987
2. Site Prep / Foundation / Slab |  | 55000
3. Metal Building Erection + Roofing / Exterior |  | 60000
4. Rough-in (HVAC / Electrical / Plumbing / Insulation) |  | 50000
5. Drywall + Interior Finish |  | 45000
6. Interior Trim / Cabinetry / Interior Painting |  | 45000
7. Countertops / Tile / Flooring |  | 45000
8. Appliances / MEP Top-out / Fixtures |  | 40000
9. Specialty Features / Fireplace / Wood Beams |  | 30000
10. Final Punchlist / Cleaning / CO |  | 34883
Total |  | 449870