## Bandominium 2500sqft
Item # | Description | Approx. Quantity | Unit of Measure | Unit Price | Item Total
Division 1: General Requirements
1 | General Conditions | 1 | LS | 5000 | 5000
1.31 | Project Coordination (Supervision) | 9 | MO | 944 | 8500
1.33 | Architectural Plans (Bandominium + MIL Suite) | 1 | LS | 6500 | 6500
1.41 | Building Permits (2,500 sqft new build) | 1 | LS | 4200 | 4200
2.21 | Engineering (Site Surveys) | 1 | LS | 2500 | 2500
1.71 | Construction Staking | 1 | LS | 750 | 750
1.71 | Mobilization | 1 | LS | 2000 | 2000
1.51 | Temporary Power | 8 | MO | 100 | 800
1.51 | Temporary Water | 8 | MO | 63 | 500
1.52 | Sanitary Facilities (Port-A-Johns) | 8 | MO | 93 | 740
T | Termite Pre-Treat | 2500 | SF | 0.15 | 375
1.74 | Progress Cleaning | 1 | LS | 2500 | 2500
1.74 | Final Cleaning | 1 | LS | 1500 | 1500
1.74 | Waste Management | 1 | LS | 2000 | 2000
|  |  |  | Division Total: | 37865
Division 2: Sitework
2.31 | Site Prep / Grading (house pad + drainage) | 1 | LS | 7500 | 7500
|  |  |  | Division Total: | 7500
Division 3: Concrete Foundation (Monolithic Slab)
3.11 | Slab Material | 2500 | SF | 6 | 15000
3.12 | Slab Labor | 2500 | SF | 2 | 5000
3.13 | Concrete Forming Material (Incl. Reinforcement) | 1 | LS | 4200 | 4200
3.14 | Pump Truck | 1 | LS | 1800 | 1800
3.15 | Masonry Sand | 1 | LS | 800 | 800
|  |  |  | Division Total: | 26800
Division 4: Metal Building Structure (Post-Frame)
4.11 | Metal Building Package / Kit (engineered post-frame, 2,500 sqft -- steel columns, rafters, purlins, metal wall panels) | 2500 | SF | 11.2 | 28000
4.12 | Metal Building Erection Labor | 2500 | SF | 5.6 | 14000
|  |  |  | Division Total: | 42000
Division 5: Roofing & Gutters
5.11 | Metal Roofing Material (26-ga R-Panel, ~2,950 sqft roof area) | 30 | SQ | 400 | 12000
5.12 | Metal Roofing Labor | 30 | SQ | 217 | 6500
5.13 | Gutter Material (6" seamless aluminum) | 280 | LF | 8.93 | 2500
5.14 | Gutter Labor | 280 | LF | 4.29 | 1200
|  |  |  | Division Total: | 22200
Division 6: Exterior Finish
6.11 | Exterior Siding / Panel Accent Material (board & batten at gables + entry) | 1 | LS | 4500 | 4500
6.12 | Exterior Trim Material | 1 | LS | 3800 | 3800
6.13 | Exterior Trim Labor | 1 | LS | 2500 | 2500
6.14 | Exterior Doors (Main x2, MIL private entry x1, Garage pass-door x1) - ALLOWANCE | 4 | EA | 1375 | 5500
6.15 | Windows (14 units, vinyl double-pane) - ALLOWANCE | 14 | EA | 857 | 12000
6.16 | Garage Door (2-car, 16x7 overhead, insulated) | 1 | EA | 2800 | 2800
|  |  |  | Division Total: | 31100
Division 7: Insulation (Closed-Cell Spray Foam)
7.11 | Closed-Cell Spray Foam Material (2" walls + 3" roof deck) | 5000 | SF | 2.1 | 10500
7.12 | Spray Foam Insulation Labor | 5000 | SF | 1.1 | 5500
|  |  |  | Division Total: | 16000
Division 8: Interior Finish
8.11 | Drywall - Material | 2500 | SF | 4.2 | 10500
8.12 | Drywall - Labor | 2500 | SF | 3 | 7500
8.13 | Interior Trim Material | 1 | LS | 5200 | 5200
8.14 | Interior Trim Labor | 1 | LS | 4000 | 4000
8.15 | Interior Doors (11 total -- main + MIL) - ALLOWANCE | 11 | EA | 427 | 4700
8.16 | Door Hardware | 11 | EA | 109 | 1200
8.17 | Closet Shelving Material | 120 | LF | 13.33 | 1600
8.18 | Closet Shelving Labor | 120 | LF | 7.08 | 850
|  |  |  | Division Total: | 35550
Division 9: Cabinetry & Countertops
9.11 | Kitchen Cabinets - Main House (semi-custom) - ALLOWANCE | 1 | LS | 11000 | 11000
9.12 | MIL Kitchenette Cabinets - ALLOWANCE | 1 | LS | 2500 | 2500
9.13 | Bathroom Vanities (3: master double, guest single, MIL single) - ALLOWANCE | 3 | EA | 1167 | 3500
9.14 | Cabinet & Drawer Hardware | 1 | LS | 800 | 800
9.15 | Countertop Material (granite/quartz -- all areas) - ALLOWANCE | 1 | LS | 8500 | 8500
9.16 | Countertop Labor | 1 | LS | 2200 | 2200
|  |  |  | Division Total: | 28500
Division 10: Tile Work
10.11 | Tile Material & Labor (3 shower surrounds + kitchen backsplash) - ALLOWANCE | 1 | LS | 8500 | 8500
10.12 | Shower Door - Master Bath (semi-frameless) | 1 | EA | 900 | 900
10.13 | Shower Door - MIL Bath (semi-frameless) | 1 | EA | 900 | 900
|  |  |  | Division Total: | 10300
Division 11: Flooring & Painting
11.11 | Interior Paint Material | 2500 | SF | 1.12 | 2800
11.12 | Interior Paint Labor | 2500 | SF | 2.32 | 5800
11.13 | LVP Flooring Material (standard 6mm) - ALLOWANCE | 2500 | SF | 4 | 10000
11.14 | LVP Flooring Labor | 2500 | SF | 1.6 | 4000
|  |  |  | Division Total: | 22600
Division 12: Plumbing
12.11 | Plumbing Material & Labor (3 baths + 2 kitchens, full rough-in + finish) | 1 | LS | 16500 | 16500
12.12 | Plumbing Gas Materials and Labor (ranges, water heaters, fireplace, dryer) | 1 | LS | 3500 | 3500
12.13 | Plumbing Fixtures (3 bath sets + 2 kitchen sinks) - ALLOWANCE | 1 | LS | 7500 | 7500
12.14 | Water Heaters (2x Tankless: 7 GPM main + 4 GPM MIL) | 2 | EA | 1400 | 2800
|  |  |  | Division Total: | 30300
Division 13: Electrical
13.11 | Electrical Material (200A main panel + 100A MIL sub-panel + all wiring) | 1 | LS | 9000 | 9000
13.12 | Electrical Labor | 1 | LS | 8500 | 8500
13.13 | Electrical Conduit (garage + utility areas) | 1 | LS | 1500 | 1500
13.14 | Lighting Fixtures - ALLOWANCE | 1 | LS | 9000 | 9000
|  |  |  | Division Total: | 28000
Division 14: HVAC
14.11 | HVAC System - Main House (3-ton central heat pump, air handler, ductwork) | 1 | LS | 14500 | 14500
14.12 | Mini-Split System - MIL Suite (12,000 BTU, wall mount + condenser) | 1 | EA | 3500 | 3500
|  |  |  | Division Total: | 18000
Division 15: Appliances
15.11 | Kitchen Appliances - Main (gas range, French door fridge, dishwasher, microwave) - ALLOWANCE | 1 | LS | 6500 | 6500
15.12 | Kitchen Appliances - MIL Suite (24" compact gas range + mini-fridge) - ALLOWANCE | 1 | LS | 2000 | 2000
15.13 | Laundry Appliances (front-load washer + dryer) - ALLOWANCE | 1 | SET | 2200 | 2200
|  |  |  | Division Total: | 10700
Division 16: Site Improvements
16.11 | Covered Front Porch (12x20 concrete slab + 4 steel posts + metal roof tie-in) | 240 | SF | 27.08 | 6500
16.12 | Driveway (gravel base ~200 LF + 20x20 concrete apron at garage) | 1 | LS | 4500 | 4500
16.13 | Landscaping / Sodding (~4,000 sqft immediate yard) | 4000 | SF | 1.38 | 5500
16.14 | Water Service (tap fee + meter box + service line to building) | 1 | LS | 3500 | 3500
|  |  |  | Division Total: | 20000
Division 17: Bandominium Specialty Features
17.11 | Exposed Wood Beam Material (living room + kitchen, 6 beams stained) | 1 | LS | 2200 | 2200
17.12 | Exposed Wood Beam Installation Labor | 1 | LS | 1000 | 1000
17.13 | Fireplace Material (propane insert + surround framing) | 1 | LS | 2500 | 2500
17.14 | Fireplace Labor | 1 | LS | 1200 | 1200
17.15 | Generator Transfer Switch / Hookup (for owner-furnished generator) | 1 | LS | 1800 | 1800
17.16 | Smart Home / Security Rough-In (camera x4, doorbell, thermostats) | 1 | LS | 2000 | 2000
|  |  |  | Division Total: | 10700
| TOTAL ESTIMATE |  |  |  | 449870
| Cost Per Sqft (2,500 sqft) |  |  |  | 179.95